## Slide 1
PRODUCT ROLLOUT · INTERNAL TEAM PLAN
AI Academy & AI Film Studio
Two revenue engines, one AI toolchain — Q3–Q4 2026
Cora AI Gateway
openIP
Cora AI Film Studio
Owner Founder Horizon Q3 → Q4 2026 Status Draft for review

## Slide 2
THE PICTURE
Two engines, one AI toolchain
ENGINE A
AI Academy — OPC training
Online + offline classes and digital content that teach people to run as AI-powered one-person companies.
Pays Learners, then B2B / edu partners Tools Cora AI Gateway (Chat · Cowork · Video Studio) + openIP Revenue Course fees + recurring tool subscriptions
ENGINE B
AI Film Studio
AI-made films, two paths: train OPCs to make films, and produce films for enterprise / SME with investment raised per movie.
Tool Cora AI Film Studio (separate) Pays Enterprise / SME clients; per-film backers Revenue Production fees + per-film funding + licensing
The flywheel Academy → OPCs on Cora AI Gateway + openIP (recurring) → creators monetize on openIP → top OPCs staff the Film Studio → films market the next cohort.

## Slide 3
PRODUCT ARCHITECTURE
Which tool does what
Cora AI Gateway
OPC · everyday AI work
Chat — general AI assistant
Cowork — agentic AI work
Video Studio — short reels & content
LIVE
openIP
OPC · monetization
Creator-IP tokenization
Fiat storefront + AI-clone
KOL terminal (SEA / WebTVAsia)
LIVE
Cora AI Film Studio
Film Studio · premium reels + film
Studio-grade production
Premium reels AND full films
openIP monetizes the film IP
BUILT
Cora AI Film Studio: up to 80% cost reduction — same top-notch quality
Two video lanes everyday reels & AI work → Cora AI Gateway · premium reels + films → Cora AI Film Studio · monetize → openIP

## Slide 4
WHO WE SERVE
The three OPC segments
1
Graduates (S1)
Want an AI career, or no job after graduation
OFFER
AI Career Accelerator — cohort, high volume, scholarship / income-share
2
Professionals, 35–55 (S2)
New to AI; want it for work or to open a business
OFFER
AI for Professionals / "Second Act" — premium, offline, HRD Corp claimable
3
Influencers / KOL (S3)
Monetize audience & content; make AI films
OFFER
Creator Monetization + AI Studio — revenue-share, done-with-you

## Slide 5
AI ACADEMY · THE PRODUCT
The course value ladder
1
AI & OPC Discovery
2 hours · online
RM999 RM299
first 20 seats
2
OPC Launch Bootcamp
2 weeks · online + lab
RM3,999
S1 scholarship RM1,799
3
AI OPC Certificate
1 year · cohort + mentorship
RM18,000
RM1,500/mo · S1 RM12,000
4
AI OPC Diploma
2 years · + practicum
RM32,000
RM16,000/yr
5
AI OPC Mastery — Founder Track
4 years · + paid studio work
RM48,000
RM12,000/yr
EVERY RUNG BUNDLES THE OPC TOOLS
Cora AI Gateway + openIP come bundled at every rung — so course revenue converts into recurring tool revenue.
Per-year cost falls as commitment rises (RM18k → RM16k → RM12k/yr).

## Slide 6
AI ACADEMY · PRICING
Segment-based pricing & fixed bundles
Rung (duration)
Professionals (S2)
standard · HRD Corp claimable
Graduates (S1)
scholarship / income-share
Bundle (individual plan)
1 · Discovery (2 hr)
RM999 → RM299 (first 20)
same — top of funnel
14-day Gateway trial
2 · Bootcamp (2 wk)
RM3,999
RM1,799 / income-share
3 mo Gateway (individual)
3 · Certificate (1 yr)
RM18,000 (RM1,500/mo)
RM12,000 (RM1,000/mo)
12 mo Gateway + openIP creator
4 · Diploma (2 yr)
RM32,000 (rare for S2)
RM32,000 via income-share ★
tools + Film Studio practicum
5 · Mastery (4 yr)
RM48,000 (rare for S2)
income-share + paid studio work ★
full tools + paid work + trainer
★ Diploma & Mastery are the graduate (S1) flagship — the career / degree-alternative. Bundles use the individual (consumer) plan, never the $500/mo Growth tier — protecting ~70% B2C margin.

## Slide 7
BENCHMARK & COMPETITIVE ANALYSIS
How our pricing sits in the market
Market reference (MY / SG, 2026)
Price
Our position
MY corporate AI workshop (1–2 days)
RM2,000–8,000/pax
Bootcamp (2 wks) RM3,999 — more program, on-market
MDEC AI Skills Training
RM5,500/pax
Public-agency benchmark (HRD Corp claimable)
MY diploma programs
RM15,000–30,000
Certificate RM18k / Diploma RM32k sit in-band
MY bachelor's (UniKL AI, part-time)
≈ RM76,800 total
Mastery RM48k = accessible degree-alternative
SG short GenAI (~21 hrs)
≈ S$2,180 (nett ~S$650 subsidised)
SG runs 2–3× MY; heavy learner subsidy
MY = employer-funded (HRD Corp) → our S2 pricing targets it. SG = learner-subsidised (SkillsFuture). Our long programs sit below diplomas/degrees yet let students earn during study.

## Slide 8
AI ACADEMY · THE PRODUCT
Ascension pathways & target conversion
NOT EVERYONE CLIMBS TO THE TOP
S1 — Graduates
Ceiling: Diploma / Mastery (2–4 yr) — the flagship
S2 — Professionals 35–55
Ceiling: Certificate (1 yr)
S3 — Influencers / KOL
Ceiling: Certificate + revenue-share
Run three ascension tracks off one intro — each pointing at the ceiling that segment actually buys.
TARGET CONVERSION AT EACH STEP
5–10%
Qualified lead → Discover
20–30%
Discover → Bootcamp
15–25%
Bootcamp → Certificate
30–40%
Certificate → Diploma
30–40%
Diploma → Mastery

## Slide 9
AI FILM STUDIO · GO-TO-MARKET
Commission it, or master it
Up to 80% cost reduction
same top-notch film quality — for reels and full films
OPTION 1 · DFY
We make your film
Audience Enterprise / SME / busy KOL Offer Production service (per-film / retainer) Revenue Production fees + per-film funding + licensing Hook Up to 80% cheaper, top quality, no learning curve
OPTION 2 · DIY
You make films
Audience Ambitious OPCs (S1 flagship), creators Offer AI OPC Mastery — Founder Track + Film Studio Revenue Tuition + tool subscription + they fulfil DFY work Hook Own the capability; earn per project; join our bench
The synthesis Sell DFY to clients → fulfil with a bench of DIY-trained Mastery graduates → scale production without full-time hires. Two front doors to one tool.

## Slide 10
PERFORMANCE METRICS
North-star metric & the bridge
★ NORTH STAR
Graduates monetizing — students earning income with AI (e.g. ≥ RM500/mo)
Proves the Academy (marketing), drives Tools retention, and justifies premium pricing — at once. Financial twin: blended MRR.
X1
Student → paying tool subscriber
The flywheel's core conversion. If this breaks, we're just a course seller.
X2
Blended LTV
Course ladder LTV + tool subscription LTV per student.
X3
Graduate-earning rate
The proof metric that lowers CAC and raises pricing power.

## Slide 11
PERFORMANCE METRICS
Two scorecards: Academy vs AI Tools
SCORECARD A
AI Academy
Education economics
Intro signups (paid)
Q3 ≥100 · Q4 ≥500
CAC per intro buyer
≤ RM120
Lead → intro conv.
5–10%
Ladder ascension rate
per targets
Completion rate
≥ 70%
NPS
≥ 40
Outcome rate (job/OPC/RM)
≥ 30% @ 90d
Course LTV : CAC
≥ 3 : 1
SCORECARD B
AI Tools
Cora AI Gateway + openIP · recurring
Attach rate (activate tool)
≥ 90%
Activation @30d
≥ 60%
Post-bundle paid conv.
≥ 40%
Tool MRR / ARR
grow MoM
Monthly churn
≤ 5%
Net revenue retention
≥ 100%
openIP GMV & creators
grow MoM
Gross margin
~70% B2C

## Slide 12
Q3 2026 · Jul–Sep
VALIDATE & BUILD FOUNDATION
~4 weeks in. Prove demand with small paid pilots — not scale. Every milestone has a measurable exit.
Q3-M1
Curriculum MVP v0 — one flagship track per segment
Aug 15
Q3-M2
Cora AI Gateway "learner mode" — onboarding + usage dashboard
Aug 22
Q3-FS1
Integrate Cora AI Film Studio into our stack — bring into repo, wire access
Sep 8
Q3-M3
Pilot cohort #1 (paid, small) — blended online + offline
Sep 5–30
Q3-M4
Film PoC #1 on Cora AI Film Studio — one short, end-to-end
Sep 15
Q3-M5
openIP creator pilot — 3–5 KOLs, storefront + AI-clone live
Sep 20
Q3-M6
Monetization & compliance base — pricing + investment framing
Sep 30

## Slide 13
Q3 EXIT GATE
Go / no-go before we scale
Proceed to Q4 scaling only if ALL of these clear. Miss any one → run an October hardening sprint before spending on growth.
✓
≥ 30 paying learners
✓
≥ 70% pilot completion
✓
1 published short · known cost/min
✓
3+ live openIP creators with sales
✓
Cora AI Film Studio integrated & working
✓
Compliance memo signed

## Slide 14
Q4 2026 · Oct–Dec
SCALE & MONETIZE
Turn validated pilots into repeatable revenue, and land the first commercial film work.
Q4-M1
Curriculum v1 — all 3 tracks complete + certificate
Oct 24
Q4-M2
Cohort #2 at scale — 150–300 learners, open enrolment
Oct–Dec
Q4-M3
Offline expansion (S2) — 2–3 in-person workshops
Nov
Q4-FS2
Cora AI Film Studio — client-delivery ready (productionize for paid work)
Nov 10
Q4-M4
Film Studio commercial pilot — deliver 2 paid client films
Nov 30
Q4-M5
Per-film investment model live — compliant + 1 funded film
Dec 5
Q4-M6
openIP × Film IP — monetize one film's IP / merch / tokens
Dec 12
Q4-M7
Annual review & 2027 plan — metrics, unit economics
Dec 20

## Slide 15
Q4 TARGETS
What good looks like by December
150–300
Paid enrolments in cohort #2
≥ 60%
Learners on a recurring Cora AI Gateway plan
2 + 1
Client films delivered + 1 funded per-film
15+
Live openIP creators, growing fiat GMV

## Slide 16
GUARDRAIL
Before we promote any per-film raise
⚠ COMPLIANCE GATE — "investment per movie"
Promising profit or returns from others' effort can cross into securities territory (the Howey line). openIP's own house rule already reflects this — we speak in terms of revenue → utility / licensing, never dividends, guaranteed returns, or "invest and profit."
Get counsel to bless the structure (film-financing SOW, sponsorship, pre-sale, or licensing) AND the exact marketing language before any raise. Hard gate: Q3-M6 → Q4-M5.

## Slide 17
WHAT COULD GO WRONG
Top risks & how we hold them
Doing Academy + Film + 3 segments at once (thin team)
→ Q3 = one flagship track + one film PoC; sequence, don't parallelize
Cora AI Film Studio built but not yet in our stack/repo
→ Prioritize import + access wiring (Q3-FS1); integration, not a build; client work behind Q4-FS2
Course sells but learners don't retain on the tool
→ Build Cora AI Gateway attach into the curriculum from lesson 1
Per-film "investment" framed as securities
→ Compliance gate before any raise; counsel-approved language only
CAC too high for price-sensitive Graduates (S1)
→ Scholarship / income-share + organic & KOL funnels; keep S1 digital-first

## Slide 18
HOW THE TEAM EXECUTES
Roles, sequence & operating rhythm
WHO OWNS WHAT
Program lead
Curriculum, instructors, delivery
Growth
Funnel, ads, KOL, enrolment
Sales / ascension
Intro pitch, ladder conversions
Tools / product
Cora + openIP provisioning, dashboards
Ops / finance
Payments, LMS, CRM, KPI dashboard
BUILD SEQUENCE
1 Ship the RM299 intro first — it's the ignition.
2 Lay rails: payments, LMS, CRM, auto tool-provisioning.
3 Build the Bootcamp while intro cohorts run.
4 Outline rungs 3–5; open a waitlist / deposit.
OPERATING RHYTHM
Weekly — signups, CAC, conversion, engagement Per cohort — ascension, completion, attach Monthly — full scorecards A+B+Bridge, MRR Quarterly — LTV:CAC, NRR, North Star, reprice

## Slide 19
THIS WEEK
Immediate next actions
1
Assign a real owner to each workstream.
2
Lock the one flagship track + one segment to lead Q3 (start with cheapest reach — likely S3 / KOL).
3
Book the counsel review for film-investment framing now — long lead.
4
Bring Cora AI Film Studio into our repo/stack (Q3-FS1) — the tool exists; this enables the Film PoC.
5
Stand up the learner-usage dashboard in Cora AI Gateway.